## Sheet1
Test Case ID | Feature | Test Scenerio | Expected Result | Actual Result | Bug Type | Status
TC-001 | Application Startup | Run the frontend application | Application should compile and start successfully | Initial syntax error prevented the application from starting; issue was identified and fixed | Frontend | Pass
TC-002 | Sign In | Sign in with valid user credentials | User should successfully sign in and access the system | Sign-in functionality could not connect to the server; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-003 | User Registration | Register a new user with valid information | New user account should be created successfully | Registration failed; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-004 | Create Team | Fill in valid team information and click “Publish Team & Launch” | New team should be created and published successfully | “Publish Team & Launch” button did not respond/work | Frontend | Fail
TC-005 | Dark/Light Mode | Switch between Dark Mode and Light Mode | Application theme should change correctly | Theme changed successfully between Dark and Light Mode | No Bug | Pass
TC-006 | Browse Teams | Open and browse available teams | Available teams should be retrieved and displayed | Teams could not be loaded; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-007 | Payment History | Open the Payment History section | User payment records should be retrieved and displayed | Payment history could not be loaded; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-008 | Notifications | Open the Notifications section | User notifications should be retrieved and displayed | Notifications could not be loaded; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-009 | Edit Profile Information | Update user profile information | Updated profile information should be saved successfully | Profile information was updated successfully | No Bug | Pass
TC-010 | Password Update | Change the user account password | Password should be updated successfully | Password was updated successfully | No Bug | Pass
TC-011 | Role Switching | Click the role switching button | User role should switch successfully and an appropriate confirmation message should be displayed | Role switched successfully and a proper message was displayed | No Bug | Pass
TC-012 | Payment Audit | Click the Payment Audit button | Payment audit page/records should open and display successfully | Button responded and opened the section, but data could not be loaded; error: “Failed to fetch” | Backend/API Connectivity | Fail
TC-013 | Browse Open Teams | Click the Browse Open Teams button | Available open teams should be displayed successfully | Button worked and opened the page, but team data could not be loaded; error: “Failed to fetch” | Backend/API Connectivity | Fail
Date: 26.08.2026
Test 2(Solution of Test 1
Test Case ID | Feature | Test Scenerio | Expected Result | Actual Result | Bug Type | Status
TC-001 | Application Startup | Run the frontend application | Application should compile and start successfully | Issues Solved | Bug solved | pass
TC-002 | Sign In | Sign in with valid user credentials | User should successfully sign in and access the system | User successfully signed in and access the system | Bug solved | Pass
TC-003 | User Registration | Register a new user with valid information | New user account should be created successfully | New user account created successfully | Bug solved | Pass
TC-004 | Create Team | Fill in valid team information and click “Publish Team & Launch” | New team should be created and published successfully | New team created and published successfully | Bug solved | Pass
TC-005 | Browse Teams | Open and browse available teams | Available teams should be retrieved and displayed | Teams are succedfully fetched | Bug solved | Pass
TC-007 | Payment History | Open the Payment History section | User payment records should be retrieved and displayed | Payment history shccessfully fetched | Bug solved | Pass
TC-008 | Notifications | Open the Notifications section | User notifications should be retrieved and displayed | Notifications error successfully fetched | Bug solved | Pass
TC-012 | Payment Audit | Click the Payment Audit button | Payment audit page/records should open and display successfully | Button responded and opened the section and data sync is successfully fetched | Bug solved | Pass
TC-013 | Browse Open Teams | Click the Browse Open Teams button | Available open teams should be displayed successfully | Button worked and opened the page as well as team data successfully loaded | Bug solved | Pass
Date: 29-08-2026